## Sheet1
Phase 1 | Estimated Hours | Actual Hours Week 3 | Actual Hours Week 4 | Actual Hours Week 5 | Actual Hours Week 6 | Actual Hours Week 7
Log-In/Registration | 10 | 6 | 4 | 0 | 0 | 0
Search UI | 10 | 8 | 0 | 0 | 0 | 0
CRN Query to Classes DB | 2 | 3 | 0 | 0 | 0 | 0
Class Addition DB Set-Up | 1 | 1 | 0 | 0 | 0 | 0
Complete "Current User" Profile UI | 10 | 0 | 8 | 2 | 0 | 0
Setup Email Verification | 2 | 0 | 1 | 1 | 0 | 0
Enable Logout | 2 | 0 | 2 | 0 | 0 | 0
Create Function to Pull Profile | 1 | 0 | 1 | 0 | 0 | 0
Class Roster Back End | 2 | 0 | 0 | 2 | 0 | 0
Complete "Current User" Back End | 5 | 0 | 0 | 3 | 0 | 0
Classes Display UI | 2 | 0 | 0 | 2 | 0 | 0
Classes Display Back End | 2 | 0 | 0 | 2 | 0 | 0
Finish "Other User" Profile | 4 | 0 | 0 | 0 | 4 | 0
Front End "Clean-Up" | 3 | 0 | 0 | 0 | 3 | 0
Actual Hours | 56 | 18 | 16 | 12 | 7 | 0
Estimated Hours | 56 | 44.8 | 33.6 | 22.4 | 11.2 | 0