## Issues
Item # | Status | Associated Design Entity | Issue Type | Brief Description | Resource | Date identified | Plan date to resolve | Date of last update | Status of resolution / comments
1 | In progress | Signup Screen | I: Issue | When Signing up for the first time, users miss the Toast "Registered Sucessfully". We need to make it more obvious or change the way we notify users | None | 2018-05-24 | TBD | 2018-05-27 | Not Completed
2 | In progress | Signup Screen | I: Issue | Insuffecient Toast Notifications | None | 2018-05-24 | TBD | 2018-05-27 | Not Completed
3 | In progress | Signup Screen | A: Action Item | Search Button still viewable from Users | None | 2018-05-24 | TBD | 2018-05-27 | Not Completed
4 | In progress | Signup Screen | I: Issue | Still able to sign into application without comfirming Email Verification | None | 2018-05-24 | TBD | 2018-05-27 | Not Completed
5 | In progress | User Profile | I: Issue | Can not see the user's information without signing up for a class first | None | 2018-05-24 | TBD | 2018-05-27 | Not Completed
6 | In progress | User Profile | I: Issue | Bug* After adding a class to to the User Profile, the user needs to sign out completely before being able to see their information | None | 2018-05-24 | TBD | 2018-05-27 | Not Completed
7 | In progress | Search Screen | I: Issue | The User clicks on the wrong information, solutions include: Make the Search Bar more noticible, or remove the text underneath | None | 2018-05-24 | TBD | 2018-05-27 | Not Completed
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Meta
Status | Issue Type
New | I: Issue
In progress | A: Action Item
Complete