## Sheet1
Phase 1 | Estimated Hours | Actual Hours Week 3 | Actual Hours Week 4 | Actual Hours Week 5 | Actual Hours Week 6
Log-In/Registration | 10 | 6 | 4 | 0
Search UI | 10 | 8 | 0 | 0
CRN Query to Classes DB | 2 | 3 | 0 | 0
Class Addition DB Set-Up | 1 | 1 | 0 | 0
Complete "Current User" Profile UI | 10 | 0 | 8 | 2
Setup Email Verification | 2 | 0 | 1 | 1
Enable Logout | 2 | 0 | 2 | 0
Create Function to Pull Profile | 1 | 0 | 1 | 0
Class Roster Back End | 2 | 0 | 0 | 2
Complete "Current User" Back End | 5 | 0 | 0 | 3
Classes Display UI | 2 | 0 | 0 | 2
Classes Display Back End | 2 | 0 | 0 | 2
Actual Hours | 49 | 18 | 16 | 12 | 0
Estimated Hours | 49 | 36.75 | 24.5 | 12.25 | 0