## Sheet1
Phase 1 | Estimated Hours | Actual Hours Week 3 | Actual Hours Week 4 | Actual Hours Week 5
Log-In/Registration | 10 | 6 | 4
Search UI | 10 | 8 | 0
CRN Query to Classes DB | 2 | 3 | 0
Class Addition DB Set-Up | 1 | 1 | 0
Complete "Current User" Profile UI | 10 | 0 | 10
Setup Email Verification | 2 | 0 | 1 | 1
Enable Logout | 2 | 0 | 2
Create Function to Pull Profile | 1 | 0 | 1
Class Roster Back End | 2 | 0 | 0 | 2
Actual Hours | 40 | 18 | 18 | 1
Estimated Hours | 40 | 26.6667 | 13.3333 | 0